## Joint
Joint Task Jornel and Frank
Task | 1 | 2 | 4 | 8 | Status
| Improvement | New Task | House Keeping | Documentation | DOING | DONE | Tested by:
Documentation of API List |  |  |  | 1
Registration | 1
Organization and Command Center Diffent | 2
Reconnecting to all units when dispatcher disconnect | 4
Automation of Enroute | 8
Notification | 16 | [6 empty] | Less display for less loading (based on date)
Cleaning of Data Base |  |  | 32

## Frank
Frank Task
Task | 1 | 2 | 4 | 8 | Status
| Improvement | New Task | House Keeping | Documentation | DOING | DONE
Disconnect (Automatic Connection) | 1
Dispatcher cannot be connected once all assest has been deployed | 2
Log-in reload.. Of responders | 4
Restrictions | 8
Live map of responders |  |  | 16
Recording |  |  | 32
Separate video of volunteer during connection of call taker |  |  | 64
Announcement | 128

## JOrnel
Jornel Task
Task | 1 | 2 | 4 | 8 | Status
| Improvement | New Task | House Keeping | Documentation | DOING | DONE
Email Auto Populate | 1
Responder Profilling | 2
Input all Barangays in Philippines | 4
Ranking | 8

## NEW Task
| 1 | 2 | 4 | 8
Task | Improvement | New Task | House Keeping | Documentation
All crew/responders/ vehicle |  | 1
EMD guide |  | 2
Fire Guide |  | 4
Law inforcement Guide |  | 8
Enroute to Hydrant
Enroute to Medical |  | 16
Enroute to Police Precint |  | 32
Task/ Mission of Responders |  | 64
Incident Command System |  | 128

## Infra
Hardware / Infra
VPN | 1
Stun/Turn | 2
Server Video/Gamefication | 4
Bac-up servers | 8
Multiple SIM for texting and Calling | 16

## StraMa
GUARDIAN Command and Control Computer Aided Dispatching and Civilian Incident Reporting as of DECEMBER 7, 2018
|  |  | # | System Updates | Call Taker | Dispatcher | Admin | Mobile App |  | Remarks | Target | Priority |  | Actual 2018 |  | Projected 2019
Legend: | [7 empty] | Volunteer | Responder |  |  | Frank | Jornel | Costs | Revenue | Costs | Revenue | Profit
| Done | TODO | 1 | Registration | [6 empty] | 2018-12-01 | 1 | 1
| On-going | Done but Need Refinements | 2 | Notification | [6 empty] | 2019-01-01 | 256 | 256
|  |  |  | IOS version | [6 empty] | 2019-03-01
|  |  | 3 | Follow Me | [6 empty] | 2018-12-01 | 2 | 2
|  |  | 4 | Incident Reporting
|  |  | 4.1 | Online
|  |  | 4.2 | Offline
|  |  | 5 | GSM Gateway:
|  |  | 5.1 | SMS
|  |  | 5.2 | USSD | [5 empty] | TBA
|  |  | 6 | Call Flow | [6 empty] | 2018-12-01 | 4 | 4
|  |  | 7 | Reconnection | [6 empty] | 2018-12-01 | 8 | 8
|  |  | 8 | Recording
|  |  | 8.1 | PBX/GSM | [6 empty] | 2018-12-01 | 16 | 16
|  |  | 8.2 | WebRTC | [6 empty] | 2018-12-01 | 32 | 32
|  |  | 8.3 | Conference | [6 empty] | 2018-12-01 | 64 | 64
|  |  | 8.4 | Archive Server
|  |  | 9 | Dispatching
|  |  | 9.1 | Incident Handling | [6 empty] | 2019-01-01 | 512 | 512
|  |  | 9.2 | Multiple Incident | [6 empty] | 2019-01-01
|  |  | 9.3 | Routing | [6 empty] | 2019-01-01 | 1024 | 1024
|  |  | 10 | Conference | [6 empty] | 2018-12-01 | 128 | 128
|  |  | 11 | ROIP | [6 empty] | 2019-01-01 | 2048 | 2048
|  |  | 12 | Reports
|  |  | 13 | Map
|  |  | 13.1 | Online
|  |  | 13.2 | Offline | [5 empty] | TBA
|  |  |  | Video Tutorial | [6 empty] | 2019-01-01
|  |  | 14 | GPS
|  |  | 15 | VPS | [5 empty] | TBA
|  |  | 16 | UI/Look and Feel | [5 empty] | TBA
|  |  | 17 | Live Map | [6 empty] | 2019-01-01 | 4096 | 4096
|  |  | 18 | Chating | [5 empty] | TBA
|  |  | 19 | Photo Share | [5 empty] | TBA
|  |  | 20 | FB Share | [5 empty] | TBA
|  |  | 21 | Gamification | [6 empty] | 2019-01-01 | 16384 | 16384
|  |  | 22 | Camera Selection | [6 empty] | 2019-01-01 | 8192 | 8192
|  |  | 23 | Systems for 7coretech
|  |  | 23.1 | Project Management | [6 empty] | 2019-04-01
|  |  | 23.2 | Time Tracker | [6 empty] | 2019-04-01
|  |  | 23.3 | Others | [5 empty] | TBA
[13 empty] | Total: | 0 | 0 | 0 | 0 | 0